## Process Flow
CHATBOT PROCESS DEFINITION
PHASES | ACTIVITIES | INPUTS | OUTPUTS | TOOLS & TECHNIQUES
Initiating | Understanding Organization Requirements | Brainstorming with Business Organization & Domain Experts | Objective Definition -Key Success Criteria - Desirability - Feasibility - Viability Bot proposal Litmus test Does the bot easily solve the user’s problem with the minimum number of steps? Does the bot solve the user’s problem better/easier/faster than any of the alternative experiences? Does the bot run on the devices and platforms the user cares about? Is the bot discoverable? Do the users naturally know what to do when using it? | Meetings / Emails
Planning | Effective Requirement Gathering | Discussions with Business Domain experts & SMEs using existing logs/fact-based analysis for driving towards key uses cases | Business Use Cases | Requirement & Design Research
| Identifying Conversation Patterns | All Stakeholder meeting - Project Sponsorer, SME, User based represntatives, Tech Team | Conversations Patterns Identification | Requirement & Design Research
| Personality Building of Bot | All Stakeholder meeting - Project Sponsorer, SME, User based represntatives, Tech Team | Bot Persona Profile | Requirement & Design Research
| Technology Support Identification | SME and Tech Team Discussions | Mapping of Conversation Type with Bot Service | Requirement & Design Research
| Intents Definitions | SME and Tech Team Discussions | Busiess Intents, LUIS Intents | Requirement & Design Research
| Coversational Flow Definition | SME and Tech Team Discussions | Convesational Flow | Requirement & Design Research
| Define "Testing Utterances" and "Training Utterances" | SME and Tech Team Discussions | Utterances Definition | Requirement & Design Research
Executing | Development of Knowledge Model | Use Cases | QnA, LUIS or Both | Knowledge Model Development
| Engineering of the Bot | Use Cases | Bot UI Layout and Convesational Flow Development | Bot Framework
| Integration with APIs | LoB API Touchpoints and Cognitive Services API Touchpoints | Bot Interation | Bot Framework
| Test the Bot | Test Utterances | Test Case Results | Bot Framework
| Deployment of Bot | Bot Codebase + Integration API Endpoints | Bot Endpoint URLs, Integration with right Channel | Selected Channel
Monitering and Controlling | Active Learning | Log Files of Utteracnes | Modifications Required | Bot Framework
| Modify the bot source and re-deploy the Bot | Modifications | Updated Model | Bot Framework
Closing | Publish the Bot Evnolution and Future Road Map | SME and Tech Team | Road Map Definition

## Understanding Org Reg
Desirability | Does this bot includes the human factors (is there a human need for this innovation? Or are we making this bot for the sake of making a bot?)
Feasibility | Is this bot technically feasible ( is the technology available to actaully do?
Viabilty | Is this project financially viable (is this sustainable from a business perspective) ?

## Conversational Patters
Conversational Patterns
Type | Description | Tech Component
One-Turn FAQ | These are general FAQ style answers that is based on one-turn responses. | QnA Maker
Intelligent Notification | This is a notification pattern because it is not in response to any query initiated by the user. Design guidance suggests caution when it comes to the bot providing proactive notification. | Proactive Bot
One-Turn Intelligent Response | These are also one-turn responses which don’t typically have a follow-up or additional conversational flow. These are “intelligent” terms as they need to be provided within the context of a conversation or activity. For example, a customer may ask, what time does flight XX065 leave LAX today? | LUIS
Contextual Guided Assistance | In this scenario, context is associated with the page/URL the user is on as opposed to who the user is and would like the bot to be able to answer questions within this context of the page/URL. | QnA Maker with State management
Multi-Turn Process Guidance | This is a unique scenario within the users’ domain - there are a number of process flows established that a bot can be enabled to do a user walk-through. While these are multi-turn dialog scenarios, they are not truly conversational as the user responses are restricted to Yes/No only with potentially an option to opt out or cancel the guided assistance. | QnA Maker with Flow handling Code
Multi-Turn Conversational Task Completion | This is a multi-turn conversational pattern typically leading to a task completion scenario. In this type of pattern, the user is not restricted to fixed responses and can potentially provide free-form natural language response. The bot will need to interpret this within the context of the process the user is in. | Advanced LUIS with State Management

## Personality Building
Chatbot Personality Profile
Age | Goals | Personality |  |  | Target Users
Occupation | 1 | Extrovert | (or) | Introvert
Residence | 2 | Sensing | (or) | Intuition
User Leve | 3 | Thinking | (or) | Feeling
Gender | 4 | Juding | (or) | Perceiving
Bio of Bot |  | Pain Points |  |  | Character
Sample Avatar ( Your Brand Promotion )

## Intents
Business Domain
Business Intent 1 | Business Intent 2 | Business Intent 3 | Business Intent 4 | Business Intent 5 | Business Intent 6
LUIS Intent 1
LUIS Intent 2
LUIS Intent 3
LUIS Intent 4
None Intent

## Entities List
Entities List
Entity Name | Entity Name | Entity Type | Intents Associated

## Sample Utterances and Reponse
Questions | Standard Response | Follow up question from chatbot | User Response/Question | Follow up question/response from chatbot | Details to get from the user for further processing? | Link (Please provide the full link) | Should we send an email to the support team?
Note on C31: Ohood Bin Hader: Not follow up question
Note on B56: Ohood Bin Hader: As of now